Agenda
Friday 8 February 2016 09:00-15:00, ESRIN, Room H, Building 9
Participants : PPM, JFP, Antoine and Abderrahim for Ifremer, Igor Ezau for NERSC, Hayley for PML (webex)
Project status summary (JFP)
Progress on WP3 (Abderrahim)
- user handbook
- best flux estimate
- structure of flux assessment report
- calculation of ocean heat content
Report on validation activities and plans (Abderrahim on behalf of Serguey, Carol Anne Clayson)
Flux validation by triple collocation (Igor Ezau)
Progress from PML – Using ocean colour and optics to evaluate ocean heat flux (Hayley)
Demonstration of flux intercomparison tool (Antoine)
Future meetings and AOB
Review of actions

---
Progress summary (1)
- WP2 : reference dataset generation
  - Preliminary product handbook provided in September (reference dataset)
  - Updated version is being finalised
    - General introduction on flux calculation
    - Improvement to estimation and best estimate product
    - Validation ressources and comparisons
- WP3 : Product generation, Intercomparison and uncertainty characterization
  - Best estimate ongoing (3.1) – 3 years of data produced
  - PDF estimation => code provided to Ifremer (fortran) and application to OHF data
  - Ensemble analysis : definition of the ensemble operator
  - Product evaluation & error characterization
    - Triple colocation (NERSC presentation)
    - Revision of cage concept wrt to available data
      - application of Karina ocean heat content calculation on Argo profile data
      - Collection of model outputs for lateral fluxes done
    - Using ocean colour and optics to evaluate ocean heat flux (Hayley)
    - Calculation of climatology of light penetration (Hayley)

---
Progress summary (2)
- WP4 : data portal, TEP concept - online crowdsourcing applications (Antoine) :
  - Flux generator
    - Statistics vs buoys are returned to the user in addition to the result
    - New inputs available (for rain)
    - Additional flux parametrizations yet to be implemented
  - New application : intercomparison of fluxes

---
Delivrables (1)
WP	Doc ref.	Description	Responsible	Due Date	Status
Scientific Requirements Consolidation
1	D1.1	Requirement Baseline Document	A Bentamy IFREMER	KO+4	V2.1 provided
Reference Dataset Generation
2	D2.1	Reference Dataset	A Bentamy IFREMER	KO+6	V1.0 provided
Product generation, inter-comparison and uncertainty characterisation
3	D3.1	Flux Assessment Report	K. Von Schuckmann	KO+11 / KO+24	ongoing
3	D3.2	Product Handbook	A Bentamy IFREMER	KO+10 / KO+23	V1.0 provided / V2.0 finalised
3	D3.3	Flux Product Dataset	A Bentamy IFREMER	KO+10 / KO+21	V1.0
Data Portal Development
4	D4.1	Data Portal / initial version at KO+3 for project communication, with presentation content, deliverables,blog,... Updated regularly then.	JF Piollé IFREMER	KO+3 / KO+8 / KO+14 / KO+18 / KO+24	v1 provided

---
Delivrables (2)
Strategic Development
5	D5.1	Scientific Roadmap	B Chapron IFREMER	KO+6 KO+18
Outreach and coordination
6	D6.1	Outreach Material	A Bentamy IFREMER	KO+11 KO+24	Published newsletter & presentations
6	D6.2	Final Workshop Report	A Bentamy IFREMER	KO+24
6	D6.6	Biannual newsletter	R Danielson NERSC	Every 6 months	Being finalised
6	D6.7	Project brochures	R Danielson NERSC	Every 6 months	Being finalised
Project management
6	D6.3	Project Management Plan (PMP)	JF Piollé IFREMER	KO+1	provided
6	D6.4	Executive Monthly Progress Report (MR)	JF Piollé IFREMER	KO+1, every month then	3-monthly
6	D6.5	Actions database (ADB)	JF Piollé IFREMER	KO+1, every month then	updated

---
Representation at meetings
Workshop	Attendant	Status
Challenges of the surface energy budget and proposed ways forward, K. von Schuckmann, S. Josey, S. Gulev, K. Trenberth, C.-A. Clayson, P.-P. Mathieu, M. Wild / EGU, Vienna, 12-17 April 2015	K Von Schuckmann	Presented
The Net Energy Budget at the Surface Interface of the “Cold Tongue” Region, Abderrahim Bentamy, Rachel T. Pinker, Banglin Zhang, Anita D. Rapp and Yingtao Ma. / EGU (European General Assembly 12 – 17 April 2015, Vienna Austria)	R. Pinker (OHF expert)	Presented
Towards Homogenization of Scatterometer Wind Retrievals, Abderrahim Bentamy, Semyon A. Grodsky, Bertrand Chapron, Anis Elyouncha / IOVWST (19 - 21 May 2015 Portland USA)	A Bentamy	Presented
Session “The Earth’s energy imbalance and exchanges at the atmosphere-ocean interface: from fundamental research to societal concern” / "Our common future under climate change", Paris, 7-10 July 2015, http://www.commonfuture-paris2015.org/	K Von Schuckmann	Presented
joint CLIVAR RF CONCEPT-HEAT/CLIVAR GSOP/COST ES1402 workshop / UK Met Office, Exeter, 28 Sept.-02 Oct.	A Bentamy K Von Schuckmann	Presented
SOOS - Air-Sea Fluxes for the Southern Ocean: Strategies and Requirements for Detecting Physical and Biogeochemical Exchanges, Frascati, Italy, September 21-23, 2015	A Bentamy / S Gulev / C A Clayson	Presented
GEWEX (Earth Observation for Water Cycle Science 2015 20th-23rd October 2015 ESA-ESRIN, Italy)	A Bentamy	Presented
Oceanflux GHG & Ocean Heat Flux : an open collaborative research framework for ocean fluxes , / EO Science 2.0	A Grouazel	Presented

---
Payment plan
Payment	Deliverables	Due date	Status
1	D4.1	10/2014	Paid
2 (CDR)	D1.1, D2.1, D5.1	03/2015	To be claimed
3	D4.1, D3.2, D3.3, D3.1, D6.1	07/2015
4	D4.1, D5.1	01/2016
Final	D3.1, D3.2, D3.3, D4.1, D6.1, D6.2	07/2016

---
ID	RESPONSIBLE	DESCRIPTION	OPEN	DUE DATE	STATUS	COMMENT
1	IFREMER/AB	Provide MoM from Paris meeting PM1	26/01/15		Closed	Done
2	IFREMER/JFP	Workpackage to be renamed conforming to IT ESA SoW tasks	26/01/15		Closed	Done in updated PMP
3	IFREMER/AG	Add MERRA reanalyzes to reference dataset	26/01/15		Closed
5	IFREMER/AB	Double check the product rights and especially ERA Interim	26/01/15		Closed
6	IFREMER/AG	Double check the version of each product and the associated DOI (if exists)	26/01/15		Closed	Done
7	IFREMER/AB	Provide the accuracy requirements for LHF and SHF. The latter would be derived from peer review publications and from scientific project reports (e.g. http://lists-ioc-goos.org/goos-strategic-mapping-graphic/ )	26/01/15		Closed	Ongoing in RB
8	IFREMER/AG	Circulate the methods aiming at the homogenization of the flux products	26/01/15		Closed	ICD document has been written for format. Further discussion needed for resampling methods.
9	IFREMER/AG	Foster interaction between NERSC and IFREMER aiming at comprehensive use of data and procedures including cloud procedure, Felyx, collocation, statistics	26/01/15		Closed	Ongoing
10	IFREMER/AB	Contact Dr Lisan YU for the updated OAFlux	26/01/15		Closed	Requested but these data are still under validation and can not be distributed
11	MIO/KVS	Provide report summarizing the main tasks relied on D1.1 (services, methods, ..)	26/01/15		Closed	Ongoing in RB
12	NERSC/RD	Provide a note aiming at the clarification of work performing by NERSC in collaboration with IFREMER	26/01/15		Closed	Done in updated PMP
13	IFREMER/AG	Assessment of variable names (see CF convention)	26/01/15		Closed
14	IFREMER/AG	Check the use of zenodo	26/01/15		Closed
15	IORAS/SG	Provide method and algorithms for PDF flux analysis	26/01/15		Open
16	IFREMER/AB	Contact Dr Shawn Smith from FSU for SAMOS data	26/01/15		Closed	Done
17	IFREMER/JFP	Change project acronym from TIE-OHF to OHF	26/01/15		Closed	Done in updated PMP
18	IFREMER/AB	Provide justification for flux datasets made available for OHF project	26/01/15		Closed	Ongoing in RB